## Sheet1
Chapter Program Management Tool
Plan of Action and Reflection
*This form is completed for each activity the committee plans. |  | Fundraising Committee
Activity | SkillsUSA Dinner & Silent Auction
Description of Activity | Host a SkillsUSA Dinner & Silent Auction to raise money to assist chapter members in attending State Leadership and Skills Conference. Members will assist in selling tickets to attend the dinner as well as secure silent auction items to be sold. In addition, we will work with the Public Relations committee to promote our SkillsUSA chapter to the community.
Framework Component | Personal
Essential Element | Responsibility
Secondary Essential Element | Integrity
Target Date of Completion | 2020-03-15
Estimated Income | 1500
Estimated Expense | 500
Actual Income | 1300
Actual Expense | 540
Intentional Essential Element Learning Goal (1 SMART)
1) | 90% of chapter members can define responsibility and increase their ability to articulate it by March 20, 2020.
Activity Goals (3 SMART)
1) | By March 15, 2020, net $1,000.00 to assist members in traveling to SLSC events.
2) | Sell 100 tickets to the SkillsUSA Dinner and Silent Auction by March 10, 2020.
3) | Secure 20 items to be used in the Silent Auction by March 5, 2020.
Plan of Action |  | Who's involved |  |  | Resources
Task | Target Date | Lead | Participants | Number | Expenses | Income | Other | Status
Take 5 question responsibility pre-assessment
Teach "To Be or Not to Be Honest" to all classes (Career Essentials: Foundations) | Jan. 15, 2020 | Instructor /Advisor | All Classes | 75 |  |  | Career Essentials: Foundations
Fundraising Committee meets to determine plan of action steps and responsibility list | Jan. 15, 2020 | Committee Chair | Committee Members | 8
Introduce Responsibility tracking sheet align with activity on Responsibility from Impact (pg. 30 Levitation Activity) | Jan. 17, 2020 | Committee Members | Chapter Members | 80 |  |  | Impact
Chapter members commit to carry out items on the responsibly list | ongoing | Committee Members | Chapter Members | 80
Gain approval of administration to host event | Jan. 18, 2020 | Committee Chair | administration
Secure cafeteria for event | Jan. 20, 2020 | Committee Member | administration
Decide on menu for event and plan meal purchase | Jan. 22, 2020 | Committee Chair | Committee Members | 8 | 450
Create invitations for the event include how to purchase tickets | Jan. 28, 2020 | Committee Member | Committee Members | 3 | 25
Send invitations via email and post on school website and social media | Jan. 29, 2020 | Committee Member | Committee Members | 3
Form subcommittee in charge of ticket sales and deposit of money | Jan. 29, 2020 | Committee Chair | Committee Members | 4 | 50
Form subcommittee in charge of securing donations for silent auction | Jan. 29, 2020 | Committee Chair | Committee Members | 4
Facilitate Responsibility activity from the Ignite book during chapter meeting (pg 37. Consistency Always) | Feb. 1, 2020 | Committee Members | Chapter Members | 80 |  |  | Ignite
Pre silent auction paperwork | Feb. 5, 2020 | Committee Member | Committee Members | 2 | 5
Determine dinner pre crew, host crew, silent auction crew and clean up crew | Feb. 10, 2020 | Committee Chair and Members | Chapter Members | 40
Prepare signage for the event | Feb. 15, 2020 | Committee Member | Committee Members | 3 | 10
Hold the event | 2020-03-15 | Committee Members | Chapter members and guests | 150 |  | 1300
Review the responsibility lists to determine the percentage that members upheld their responsibility to the activity | 2020-03-18 | Committee Chair | Committee Members | 8
Take post responsibility 5 question assessment developed from Framework Fundamental Cards | 2020-03-18 | Instructor/Advisor | Chapter Members | 80
Celebrate with donuts and recap the event with committee members | 2020-03-20 | Instructor/Advisor | Committee Members | 8
|  |  |  | Total | 540 | 1300
|  |  |  | Profit/Loss | 760
Results/ Evaluation/ Framework
What was accomplished? How did this activity help members these skills based on the essential elements selected above? - All students were exposed to the Essential Element of integrity through the classroom activity. Chapters members and committee members were able to expand their knowledge of integrity and responsibly through the Ignite activity and by using the Responsibility Tracking sheet. Since the tracking sheet was publicly displayed, members were able to keep one another accountable as well.
Intentional Essential Element Learning Goal (1 SMART)
1) | 90% of chapter members can define responsibility and increase their ability to articulate it by March 20, 2020.
Met - 100% of chapter members could define responsibility and could articulate the importance of being responsible in the workplace March 20, 2020
Activity Goals (3 SMART)
1) | By March 15, 2020, net $1,000.00 to assist members in traveling to SLSC events.
Unmet - Even though we sold a lot of tickets, we realized after the invitations had been prepared that we did not set the ticket price high enough to meet the actual income goal of the event.
2) | Sell 100 tickets to the SkillsUSA Dinner and Silent Auction by March 10, 2020.
Met - We found selling the tickets was easy as we tied it into the silent auction and everyone got one free raffle ticket for just buying a dinner ticket.
3) | Secure 20 items to be used in the Silent Auction by March 5, 2020.
Met - The members secured 25 items but the value of each item was not very high.
Future Plans | Consider the actual costs of the dinner preparation prior to setting the ticket price to ensure adequate ticket price.
Consider including more raffles and awarding them throughout dinner to drive up onsite raffle ticket sales.
Strategize as to how to locate higher valued silent auction items. Fewer items with greater value might lead to bigger gains.